## Cover page
Group 03 Member of group: CE130377 - Nguyen Thanh Nhan CE130382 - Nguyen Truong Ky CE130252 - Nguyen Chi Linh CE130393 - Lam Thi Khanh Hang
Real-estate Testing
Test case
Date | Version | Status |  | Author | Reviewed by | Approved by
2020-03-19 | 1.0 | Finished |  | NhanNT | KyNT, LinhNC, HangLTK | NhanNT
Revision History
Date | Version | Description |  |  | Author
2020-03-20 | 1.0 | Function test cases |  |  | NhanNT
2020-03-26 | 1.1 | Function test cases |  |  | KyNT
2020-03-26 | 1.2 | Function test cases |  |  | LinhNC
2020-03-27 | 1.3 | Interface |  |  | HangLTK
Execution History
Date of Execution | Executed by |  | Build Under Test
2020-03-20 | NhanNT |  | Function test cases: Login, Create product, List product, Paging product, Edit product, View detail product, Delete product, Search product
2020-03-21 | NhanNT |  | Function test cases: Create employee, List employee, Paging employee, Edit employee, View detail employee, Delete employee, Search employee
2020-03-26 | KyNT |  | Function test cases: edit customer, delete customer, change employee's information logged.
2020-03-26 | LinhNC |  | Function test cases: View list potential customer, Confirm potential customer, View detail, Change password, logout
2020-03-27 | HangLTK |  | Interface testing

## Glossary
Glossary
Definition
Terms | Description
Function Test | Check and find different between user's requirement and real producure, include login, create product, edit product, view product, edit product, list product, paging product, search product, delete employee, create employee, add employee, edit employee, view employee's information, list employee, search employee, paging employee, delete employee, edit customer, change employee's information logged,view list potential customer, confirm potential customer, view detail potential customer, change password, logout
Interface test | Check the interface requirement

## Testcase
Group 03 Member: CE130377 - Nguyen Thanh Nhan CE000000 - Nguyen Truong Ky CE000000 - Nguyen Chi Linh CE000000 - Lam Thi Khanh Hang | [5 empty] | Number Of Test case | 47
[6 empty] | Pass | 40
[6 empty] | Fail | 7
Real-estate
ID | Tester's Name | Test Title | Sub-testing | Description | Pre-condition | Test Procedures |  | Test Data | Expected Results | Actual Result | Post-Condition | Status (Fail/Pass) | Test Priority | Date of the Test | Notes
[6 empty] | Steps to Perform | Step Expected Result
TC1 | NhanNT | Login | None | Test login form for admin | No | 1. Open admin form in browser 2. Enter username (wrong) 3. Enter password (wrong) 4. Enter or click Login button | 1.Load login page 2.Fill the username textbox 3. Fill the password textbox 4. Display error | 1. username = 'nhan'. 2. password = 'nhan'. | Error message: Username or password is wrong! | Error message: Username or password is wrong! | Return login page | Pass | High | 2020-03-20 | No
TC2 | NhanNT | Login | None | Test login form for admin | No | 1. Open admin form in browser 2. Enter username (right) 3. Enter password (wrong) 4. Enter or click Login button | 1.Load login page 2.Fill the username textbox 3. Fill the password textbox 4. Display error | 1. username = 'nhannt'. 2. password = '2'. | Error message: Username or password is wrong! | Error message: Username or password is wrong! | Return login page | Paas | High | 2020-03-20 | No
TC3 | NhanNT | Login | None | Test login form for admin | No | 1. Open admin form in browser 2. Enter username (wrong) 3. Enter password (right) 4. Enter or click Login button | 1.Load login page 2.Fill the username textbox 3. Fill the password textbox 4. Display error | 1. username = '@@@@'. 2. password = '1'. | Error message: Username or password is wrong! | Error message: Username or password is wrong! | Return login page | Pass | High | 2020-03-20 | No
TC4 | NhanNT | Login | None | Test login form for admin | No | 1. Open admin form in browser 2. Enter username (right) 3. Enter password (right) 4. Enter or click Login button | 1.Load login page 2.Fill the username textbox 3. Fill the password textbox 4. Open dashboard | 1. username = 'nhannt'. 2. password = '1'. | Go to the dashboard | Go to the dashboard | Return the dashboard page | Paas | High | 2020-03-20 | Can't go to the login page when user is logged
TC5 | NhanNT | Load list product | Only one test case | Test load all product from DB into table | Complete TC1 | 1. Open dashboard 2. Click Product in menu | 1. Open the dashboard page 2. Open the the list product page | No | Show list product | Show list product | Return list-product page | Pass | Average | 2020-03-20 | No
TC6 | NhanNT | Search product | Only one test case | Search product in list product | Complete TC2 | 1. Enter despription or dictrict into search textfield 2. Click Search or press Enter | 1. Fill search textbox 2. Show product matching with search value | search = 'Ninh Kieu' | Show all product in Ninh Kieu | Show all product in Ninh Kieu | Return list-poduct page | Pass | Average | 2020-03-20 | No
TC7 | NhanNT | Paging product | Only one test case | Paging product | Complete TC2 | Click other page in list page in bottom of page | Show product in page selected | No | Show other product in page clicked | Show other product in page clicked | Return list-product/page's number page | Pass | Average | 2020-03-20 | No
TC8 | NhanNT | Add new product | Only one test case | Test add new product | Complete TC2 | 1. Click + in list product page 2. Fill description "description" 3. Fill price "price" 4. Fill area "area" 5. Choose type in combobox "Type" 6. Choose district in combobox "District" 7. Fill position "position" 8. Fill direction "direction" 9. Fill juridical "juridical" 10. Fill Right of way "Right of way" 11. Select image from divice 12. Click button submit | 1. Open add new product 2. Fill description text box 3. Fill price text box 4. Fill area text box 5. Display "House" 6. Display "Ninh Kieu" 7. Fill position text box 8. Fill direction text box 9. Fill juridical text box 10. Right of way text box 11. Display number of image 12. Go to the list product | 1. Description = 'Near school…' 2. Price = '5000' 3. Area = '100' 4. Type = 'House' 5. District = 'Ninh Kieu' 6. Position = '15 Nguyen Viet Dung' 7. Direction = 'West' 8. Juridical = '100% residential' 9. Right of way = '13' 10. Image | Go to the last page of list product | Go to the last page of list product | Return list product page | Pass | Average | 2020-03-20 | No
TC9 | NhanNT | Add new product | Only one test case | Test add new product with description empty | Complete TC2 | 1. Click + in list product page 2. Fill description "description" 3. Fill price "price" 4. Fill area "area" 5. Choose type in combobox "Type" 6. Choose district in combobox "District" 7. Fill position "position" 8. Fill direction "direction" 9. Fill juridical "juridical" 10. Fill Right of way "Right of way" 11. Select image from divice 12. Click button submit | 1. Open add new product 2. Fill description text box 3. Fill price text box 4. Fill area text box 5. Display "Land" 6. Display "Ninh Kieu" 7. Fill position text box 8. Fill direction text box 9. Fill juridical text box 10. Right of way text box 11. Display number of image 12. Go to the list product | 1. Description = '' 2. Price = '-5000' 3. Area = '-100' 4. Type = 'Land' 5. District = 'Ninh Kieu' 6. Position = '' 7. Direction = '' 8. Juridical = 'l' 9. Right of way = '-13' 10. Invalid | Cannot complete step 2 in add new product because fill wrong data | Cannot complete step 1 in add new product because fill wrong data | Return add new product page | Pass | Average | 2020-03-20 | No
TC10 | NhanNT | Add new product | Only one test case | Test add new product with price < 0 | Complete TC2 | 1. Click + in list product page 2. Fill description "description" 3. Fill price "price" 4. Fill area "area" 5. Choose type in combobox "Type" 6. Choose district in combobox "District" 7. Fill position "position" 8. Fill direction "direction" 9. Fill juridical "juridical" 10. Fill Right of way "Right of way" 11. Select image from divice 12. Click button submit | 1. Open add new product 2. Fill description text box 3. Fill price text box 4. Fill area text box 5. Display "House" 6. Display "Ninh Kieu" 7. Fill position text box 8. Fill direction text box 9. Fill juridical text box 10. Right of way text box 11. Display number of image 12. Go to the list product | 1. Description = 'Near school' 2. Price = '-5000' 3. Area = '-100' 4. Type = 'Land' 5. District = 'Ninh Kieu' 6. Position = '' 7. Direction = '' 8. Juridical = 'l' 9. Right of way = '-13' 10. Invalid | Cannot complete step 3 in add new product because fill wrong data |  | Return add new product page | Pass | Average | 2020-03-20 | No
TC11 | NhanNT | Add new product | Only one test case | Test add new product with area < 0 | Complete TC2 | 1. Click + in list product page 2. Fill description "description" 3. Fill price "price" 4. Fill area "area" 5. Choose type in combobox "Type" 6. Choose district in combobox "District" 7. Fill position "position" 8. Fill direction "direction" 9. Fill juridical "juridical" 10. Fill Right of way "Right of way" 11. Select image from divice 12. Click button submit | 1. Open add new product 2. Fill description text box 3. Fill price text box 4. Fill area text box 5. Display "House" 6. Display "Ninh Kieu" 7. Fill position text box 8. Fill direction text box 9. Fill juridical text box 10. Right of way text box 11. Display number of image 12. Go to the list product | 1. Description = 'Near school' 2. Price = '5000' 3. Area = '-100' 4. Type = 'Land' 5. District = 'Ninh Kieu' 6. Position = '' 7. Direction = '' 8. Juridical = 'l' 9. Right of way = '-13' 10. Invalid | Cannot complete step 4 in add new product because fill wrong data | Cannot complete step 4 in add new product because fill wrong data | Return add new product page | Pass | Average | 2020-03-24 | No
TC12 | NhanNT | Add new product | Only one test case | Test add new product with position empty | Complete TC2 | 1. Click + in list product page 2. Fill description "description" 3. Fill price "price" 4. Fill area "area" 5. Choose type in combobox "Type" 6. Choose district in combobox "District" 7. Fill position "position" 8. Fill direction "direction" 9. Fill juridical "juridical" 10. Fill Right of way "Right of way" 11. Select image from divice 12. Click button submit | 1. Open add new product 2. Fill description text box 3. Fill price text box 4. Fill area text box 5. Display "House" 6. Display "Ninh Kieu" 7. Fill position text box 8. Fill direction text box 9. Fill juridical text box 10. Right of way text box 11. Display number of image 12. Go to the list product | 1. Description = 'Near school' 2. Price = '5000' 3. Area = '-100' 4. Type = 'Land' 5. District = 'Ninh Kieu' 6. Position = '' 7. Direction = '' 8. Juridical = '' 9. Right of way = '-13' 10. Invalid | Cannot complete step 7 in add new product because fill wrong data | Cannot complete step 7 in add new product because fill wrong data | Return add new product page | Pass | Average | 2020-03-20 | No
TC13 | NhanNT | Add new product | Only one test case | Test add new product with Direction empty | Complete TC2 | 1. Click + in list product page 2. Fill description "description" 3. Fill price "price" 4. Fill area "area" 5. Choose type in combobox "Type" 6. Choose district in combobox "District" 7. Fill position "position" 8. Fill direction "direction" 9. Fill juridical "juridical" 10. Fill Right of way "Right of way" 11. Select image from divice 12. Click button submit | 1. Open add new product 2. Fill description text box 3. Fill price text box 4. Fill area text box 5. Display "House" 6. Display "Ninh Kieu" 7. Fill position text box 8. Fill direction text box 9. Fill juridical text box 10. Right of way text box 11. Display number of image 12. Go to the list product | 1. Description = 'Near school' 2. Price = '5000' 3. Area = '-100' 4. Type = 'Land' 5. District = 'Ninh Kieu' 6. Position = '' 7. Direction = '' 8. Juridical = '' 9. Right of way = '-13' 10. Invalid | Cannot complete step 8 in add new product because fill wrong data |  | Return add new product page | Pass | Average | 2020-03-20 | No
TC14 | NhanNT | Add new product | Only one test case | Test add new product with juridical empty | Complete TC2 | 1. Click + in list product page 2. Fill description "description" 3. Fill price "price" 4. Fill area "area" 5. Choose type in combobox "Type" 6. Choose district in combobox "District" 7. Fill position "position" 8. Fill direction "direction" 9. Fill juridical "juridical" 10. Fill Right of way "Right of way" 11. Select image from divice 12. Click button submit | 1. Open add new product 2. Fill description text box 3. Fill price text box 4. Fill area text box 5. Display "House" 6. Display "Ninh Kieu" 7. Fill position text box 8. Fill direction text box 9. Fill juridical text box 10. Right of way text box 11. Display number of image 12. Go to the list product | 1. Description = 'Near school' 2. Price = '5000' 3. Area = '-100' 4. Type = 'Land' 5. District = 'Ninh Kieu' 6. Position = '' 7. Direction = '' 8. Juridical = '' 9. Right of way = '-13' 10. Invalid | Cannot complete step 9 in add new product because fill wrong data |  | Return add new product page | Pass | Average | 2020-03-20 | No
TC15 | NhanNT | Add new product | Only one test case | Test add new product with right of way empty | Complete TC2 | 1. Click + in list product page 2. Fill description "description" 3. Fill price "price" 4. Fill area "area" 5. Choose type in combobox "Type" 6. Choose district in combobox "District" 7. Fill position "position" 8. Fill direction "direction" 9. Fill juridical "juridical" 10. Fill Right of way "Right of way" 11. Select image from divice 12. Click button submit | 1. Open add new product 2. Fill description text box 3. Fill price text box 4. Fill area text box 5. Display "House" 6. Display "Ninh Kieu" 7. Fill position text box 8. Fill direction text box 9. Fill juridical text box 10. Right of way text box 11. Display number of image 12. Go to the list product | 1. Description = 'Near school' 2. Price = '5000' 3. Area = '-100' 4. Type = 'Land' 5. District = 'Ninh Kieu' 6. Position = '' 7. Direction = '' 8. Juridical = '' 9. Right of way = '-13' 10. Invalid | Cannot complete step 10 in add new product because fill wrong data |  | Return add new product page | Pass | Average | 2020-03-20 | No
TC16 | NhanNT | Edit product | Only one test case | Edit a product is added with all valid value | Complete TC2 | 1. Click + in list product page 2. Fill description "description" 3. Fill price "price" 4. Fill area "area" 5. Choose type in combobox "Type" 6. Choose district in combobox "District" 7. Fill position "position" 8. Fill direction "direction" 9. Fill juridical "juridical" 10. Fill Right of way "Right of way" 11. Select image from divice 12. Click button submit | 1. Open add new product 2. Fill description text box 3. Fill price text box 4. Fill area text box 5. Display "House" 6. Display "Ninh Kieu" 7. Fill position text box 8. Fill direction text box 9. Fill juridical text box 10. Right of way text box 11. Display number of image 12. Go to the list product | 1. Description = 'Near school…' 2. Price = '5000' 3. Area = '100' 4. Type = 'House' 5. District = 'Ninh Kieu' 6. Position = '15 Nguyen Viet Dung' 7. Direction = 'West' 8. Juridical = '100% residential' 9. Right of way = '13' 10. Image | Go to the page contain product is edit | Go to the page contain product is edit | Return list product page | Pass | Average | 2020-03-20 | No
TC17 | NhanNT | Detail product | Only one test case | See a detail of product | Complete TC8 | Click the information icon in row need to see detail | Show all product's information | No | Go to the detail page of product | Go to the daetail page of product | Return deatail page | Pass | Average | 2020-03-20 | No
TC18 | NhanNT | Load employee list | Only one test case | Load all of employee from DB | Complete TC1 | 1. Open dashboard 2. Click Emplyee in menu | 1. Open the dashboard page 2. Open the the list product page | No | Show employee list | Show employee list | Return list-employee page | Pass | Average | 2020-03-21 | No
TC19 | NhanNT | Search employee | Only one test case | Search a employee in employee list | Complete TC18 | 1. Enter name or phone number of employee into search textfield. 2. Click Search or press Enter | 1. Fill search textbox 2. Show employee matching with search value | phone number = '09656' | Show all of emplyees have phone number match with 09656 | Show all of emplyees have phone number match with 09657 | Return list-employee page | Pass | Average | 2020-03-21 | No
TC20 | NhanNT | Paging employee | Only one test case | Paging employee | Complete TC18 | Click other page in list page in bottom of page |  | No | Show other product in page clicked | Show other product in page clicked | Return list-employee/page's number page | Pass | Average | 2020-03-21 | No
TC21 | NhanNT | Add new Emplooye | Only one test case | Test add new employee | Complete TC18 | 1. Click + in list employee page 2. Fill name "name" 3. Fill address "address" 4. Fill email "email" 5 Fill phone "phone" 6. Choose birthday in date edit 7. Choose gender in radio button 8. Fill account "account" 9. Fill password "password" 10. Choose role in combobox | 1. Open add new product page 2. Fill name textbox 3. Fill address textbox 4. Fill email textbox 5. Fill phone textbox 6. Date selected 7. Gender clicked 8. Fill account textbox 9. Fill password textbox 10. Choose role "Employee" | 1. Name = 'Thành Nhân' 2. Address = 'Long My, Hau Giang' 3. Email = 'nhanntce130377@fpt.edu.vn' 4. Phone = '0965689616' 5. Birthday = '21/02/1999' 6. Gender = 'Male' 7. Account = 'nhannt' 8. Password = 'nhan123' 9. Role = 'Employee' | Go to the last page of list employee | Go to the last page of list employee | Return last of list-product page | Pass | Average | 2020-03-21 | No
TC22 | NhanNT | Add new Emplooye | Only one test case | Test add new employee name is empty | Complete TC18 | 1. Click + in list employee page 2. Fill name "name" 3. Fill address "address" 4. Fill email "email" 5 Fill phone "phone" 6. Choose birthday in date edit 7. Choose gender in radio button 8. Fill account "account" 9. Fill password "password" 10. Choose role in combobox | 1. Open add new product page 2. Fill name textbox 3. Fill address textbox 4. Fill email textbox 5. Fill phone textbox 6. Date selected 7. Gender clicked 8. Fill account textbox 9. Fill password textbox 10. Choose role "Employee" | 1. Name = '' 2. Address = 'Long My, Hau Giang' 3. Email = 'nhanntce130377@fpt.edu.vn' 4. Phone = '0965689616' 5. Birthday = '21/02/1999' 6. Gender = 'Male' 7. Account = 'nhannt' 8. Password = 'nhan123' 9. Role = 'Employee' | Cannot complete step 2 in add new product because fill wrong data | Cannot complete step 2 in add new product because fill wrong data | Return add new employee page | Pass | Average | 2020-03-21 | No
TC23 | NhanNT | Add new Emplooye | Only one test case | Test add new employee address is empty | Complete TC18 | 1. Click + in list employee page 2. Fill name "name" 3. Fill address "address" 4. Fill email "email" 5 Fill phone "phone" 6. Choose birthday in date edit 7. Choose gender in radio button 8. Fill account "account" 9. Fill password "password" 10. Choose role in combobox | 1. Open add new product page 2. Fill name textbox 3. Fill address textbox 4. Fill email textbox 5. Fill phone textbox 6. Date selected 7. Gender clicked 8. Fill account textbox 9. Fill password textbox 10. Choose role "Employee" | 1. Name = 'Thanh Nhan' 2. Address = '' 3. Email = 'nhanntce130377@fpt.edu.vn' 4. Phone = '0965689616' 5. Birthday = '21/02/1999' 6. Gender = 'Male' 7. Account = 'nhannt' 8. Password = 'nhan123' 9. Role = 'Employee' | Cannot complete step 3 in add new product because fill wrong data | Cannot complete step 3 in add new product because fill wrong data | Return add new employee page | Pass | Average | 2020-03-22 | No
TC24 | NhanNT | Add new Emplooye | Only one test case | Test add new employee email is empty | Complete TC18 | 1. Click + in list employee page 2. Fill name "name" 3. Fill address "address" 4. Fill email "email" 5 Fill phone "phone" 6. Choose birthday in date edit 7. Choose gender in radio button 8. Fill account "account" 9. Fill password "password" 10. Choose role in combobox | 1. Open add new product page 2. Fill name textbox 3. Fill address textbox 4. Fill email textbox 5. Fill phone textbox 6. Date selected 7. Gender clicked 8. Fill account textbox 9. Fill password textbox 10. Choose role "Employee" | 1. Name = 'Thanh Nhan' 2. Address = 'Long My, Hau Giang' 3. Email = '' 4. Phone = '0965689616' 5. Birthday = '21/02/1999' 6. Gender = 'Male' 7. Account = 'nhannt' 8. Password = 'nhan123' 9. Role = 'Employee' | Cannot complete step 4 in add new product because fill wrong data | Cannot complete step 4 in add new product because fill wrong data | Return add new employee page | Pass | Average | 2020-03-23 | No
TC25 | NhanNT | Detail employee | Only one test case | See a detail of employee | Complete TC8 | Click the information icon in row need to see detail |  | No | Go to the detail page of employee | Go to the detail page of employee | Return detail employee page | Pass | Average | 2020-03-21 | No
TC26 | KyNT | Load list Customer | Only one test case | Load all Customer | Complete TC1 | 1. Login admin page. 2. Click Customer management. | 1. login account and Open customer management page | No | Show list Customer. | Show list product. | Return list-Customer page. | Pass | Average | 2020-03-25 | No
TC27 | KyNT | Search Customer | Only one test case | Search Name customer in list Customer | Complete TC1 | 1. Enter Name search textfield 2. Click Search or press Enter | 1. Open customer management page 2. enter search string, press enter | search = 'Nhan' | Show all Customer have name Ky. | Show all Customer have Name Ky. | Return list-Customer page. | Pass | Average | 2020-03-25 | No
TC28 | KyNT | Paging list Customer | Only one test case | Paging list Customer | Complete TC1 | Click other page in list page in bottom of page | 1.Open customer management page check paging | No | Show other Customer in page clicked. | Show other Customer in page clicked. | Return list-Customer/page's number page | Pass | Average | 2020-03-25 | No
TC29 | KyNT | Delete Customer | Only one test case | Delete Customer | Complete TC1 | 1.click icon delete the same row with customer delete. 2. click OK in message box | 1. Open customer management page 2.click icon delete on right info customer delete | No | Show list customer was delete. | Show list customer was delete. | Return delete customer page | Pass | Average | 2020-03-25 | Add Button Back in delete page
TC30
TC31 | KyNT | Edit | input wrong value | Edit customer form | TC26 | 1.Enter value in name textbox. 2. click button update. | 1. click icon edit on right info customer edit. 2. edit textbox Name and click update | name = '22222' or null or valid keys space and not special character | Show message warning 'Name error format!' | 1. Accept name. 2. Show list customer. | Return list-Customer page. | FALSE | Average | 2020-03-25 | FALSE add do not check data input textbox add show message update successfull
[6 empty] | 1. Enter false Email. 2.click button update. | 1. click icon edit on right info customer edit. 2. edit textbox Email and click update | email= '22222' or 'kynt' or 'kynt10@gmail' or null | Show message warning 'Email error format!' | 1. Accept email. 2. Show list customer. | Return list-customer page. | FALSE |  | 2020-03-25
[6 empty] | 1. Enter false Phone number. 2. click button update. | 1. click icon edit on right info customer edit. 2. edit textbox Phone and click update | phone = '09656' and not special character and phone='11111111111111111' and phone='asdad' or null | Show message warnig 'phone number so long'. Show message warning 'phone number so short'. Show message warning 'phone number must be digit'. | 1. Accept phone number. 2. Show list customer. | Return list -customer page. | FALSE | Average | 2020-03-25
|  |  | input true value | Edit customer form | TC26 | 1.Enter true name. 2.Enter true email. 3.Enter true phone 4. click button update. | 1. click icon edit on right info customer edit. 2. edit textbox Name, edit textbox phone 3. edit textbox email, edit birthday, edit sex 4. click Update. Return Customer management page | name = 'truong ky' email= 'kynt@gmai.com' phone='0868772887' | Show message update successful data update into database Show list customer | 1. data update database. 2. Show list customer. | Return list-Customer page. | PASS | Average | 2020-03-25
TC32 | KyNT | Edit information current account | input wrong value | Edit info account form | TC1 | 1.Enter false value in name textbox. 2. click button update. | 1. click my information 2. edit textbox Name and click update | name = '22222' or null | Show message warning 'Name error format!' | 1. Accept name. 2. Show list customer. | Return list-Customer page. | FALSE | Average | 2020-03-25 | FALSE add do not check data input textbox add show message update successfull
[6 empty] | 1. Enter false Email. 2.click button update. | 1. click my information. 2. edit textbox Email and click update | email= '22222' or 'kynt' or 'kynt10@gmail' or null | Show message warning 'Email error format!' | 1. Accept email. 2. Show list customer. | Return list-customer page. | FALSE |  | 2020-03-25
[6 empty] | 1. Enter false Phone number. 2. click button update. | 1. click my information. 2. edit textbox Phone and click update | phone = '09656' phone='11111111111' phone='asdad' or null | Show message warning 'phone number so long'. Show message warning 'phone number so short'. Show message warning 'phone number must be digit'. | 1. Accept phone number. 2. Show list customer. | Return list -customer page. | FALSE | Average | 2020-03-25
[6 empty] | 1. Enter address. 2. click button update | 1. click my information. 2. edit address and click update | address= null | Show message warning 'address must be not null' | 1. Accept address. 2. Show current page. | Return Home-page | FALSE | Average | 2020-03-25
|  |  | input true value | Edit info account form | TC1 | 1.Enter true name. 2.Enter true email. 3.Enter true phone 4. click button update. | 1. click my information. 2. edit infor about name, address, email, phone sex, birthday. 3. click update => Customer management page | name = 'truong ky' email= 'kynt@gmai.com' phone='0868772887' | Show message update successful data update into database Show list customer | 1. data update database. 2. Show list customer. | Return list-Customer page. | PASS | Average | 2020-03-25
TC33 | LinhNC | Load potential customer list | One test case | Go to potential customer list | Complete TC1 | 1. Open page dashboard | 1. See Home page on page | No | Go to potential customer list | Go to potential customer list | Return potential customer page | Pass | Average | 2020-03-23 | No
[6 empty] | 2. Click "Potential customer" | 2. See fill dashboard
3. See all list in dashboard
TC34 | LinhNC | Search potential customer | Test true value entered | Search potential in list | Complete TC1 | 1. Click textbook "Search" in page | 1. See text book search on page | Enter value = "Vy" | Display name's potenrial customer have value "Vy" | Display all potential customer have value "Vy" on page | Return potential customer page | Pass | Average | 2020-03-23 | No
[6 empty] | 2. Enter value into textbook | 2. Textbook can enter value
[6 empty] | 3. Click search | 3. Display customer on page
TC35 | LinhNC | Search potential customer | Test wrong value entered | Seach potential in list | Complete TC1 | 1. Click textbook "Search" in page | 1. See text book search on page | Enter value = "tan" | Not potential customer display onpage | Not potential customer display onpage | Return potential customer page | Pass | Average | 2020-03-23 | No
[6 empty] | 2. Enter value into textbook | 2. Textbook can enter value
[6 empty] | 3. Click search | 3. Display customer on page
TC36 | LinhNC | Add potential customer | One test case | Add potential customer | Complete TC1 | 1. Click button "Add" on page | 1. See button "Add" on page 2. Click button "Add" | No | Display value in column "Check Sold", Display button "detail" in column Manager, button "Add" have color Green | Display value in column "Check Sold", Display button "detail" in column Manager, button "Add" have color Green | Return potential customer page | Pass | Average | 2020-03-23 | No
TC37 | LinhNC | Display detail of potential customer | One test case | See detail of potential customer on page | Complete TC1 | 1. Click button "Detail" on page | 1. See button "Detail" on page 2. Click button "Detail" on page | No | Display detail of potential customer | Display detail of potential customer | Return detail potential customer page | Pass | Average | 2020-03-23 | No
TC38 | LinhNC | See each image of product in detail | One test case | See all images of product in detail | Complete TC5 | 1. Click each image of product on detail page 2. Display image clicked | 1. See all impormation on page 2. Click image | No | Display image on page | Display image on page | Return detail potential customer page | Pass | Average | 2020-03-23 | No
TC39 | LinhNC | Back list potential customer page | One test case | See page list potential customer | Complete TC5 | 1. Click button "Back" on page detail | 1. See button "Back" on page detail 2. Click button "Back" | No | Go to potential customer list | Go to potential customer list | Return page potential customer list | Pass | Average | 2020-03-23 | No
TC40 | LinhNC | Save description | One test case | Save description of potential customer | Complete TC1 | 1. Click button "Description" 2. Enter information In textbook 3. Click "Save" | 1. See button "Description" on page 2. Click button "Description" on page 3. Enter information after click "Save" | Enter value = "aaa" | Go to page save description | Go to page save description | Return page potential customer list | Pass | Average | 2020-03-23 | No
TC41 | LinhNC | Confirm check sold | One test case | Confirm check sold | Complete TC1 | 1. Click button "Not yet" on page | 1. See button "Not yet" on page 2. Click button | No | Check sold Confirmed | Check sold Confirmed | Return page potential customer list | Pass | Average | 2020-03-23 | No
TC42 | LinhNC | Change pass word | Test true value entered | Display windown change pass word | Complete TC1 | 1. Open dashboard 2. Input new pass word 3. Confirm pass word 4. Click confirm | 1. Open dashboard 2. Input new pass word 3. Confirm pass word 4. Click confirm | Enter new pass = "123" Enter confirm = "123" | Go to dashboard | Go to dashboard | Return page potential customer list | Pass | Average | 2020-03-23 | No
TC43 | LinhNC | Change pass word | Test wrong value entered | Display windown change pass word | Complete TC1 | 1. Open dashboard 2. Input new pass word 3. Confirm pass word 4. Click confirm | 1. Open dashboard 2. Input new pass word 3. Confirm pass word 4. Click confirm | Enter new pass = "" Enter confirm = "" | Error message:Please fill out this field!!!!!! | Error message:Please fill out this field!!!!!! | Return page change password | Pass | Average | 2020-03-23 | No
TC44 | LinhNC | Change pass word | Test wrong value entered | Display windown change pass word | Complete TC1 | 1. Open dashboard 2. Input new pass word 3. Confirm pass word 4. Click confirm | 1. Open dashboard 2. Input new pass word 3. Confirm pass word 4. Click confirm | Enter new pass = "123" Enter confirm = "" | Error message:Please fill out this field!!!!!! | Error message:Please fill out this field!!!!!! | Return page change password | Pass | Average | 2020-03-23 | No
TC45 | LinhNC | Change pass word | Test wrong value entered | Display windown change pass word | Complete TC1 | 1. Open dashboard 2. Input new pass word 3. Confirm pass word 4. Click confirm | 1. Open dashboard 2. Input new pass word 3. Confirm pass word 4. Click confirm | Enter new pass = "123" Enter confirm = "1234" | Error message:Confirm password wrong!!!!!! | Error message:Confirm password wrong!!!!!! | Return page change password | Pass | Average | 2020-03-23 | No
TC46 | LinhNC | Change pass word | Test wrong value entered | Display windown change pass word | Complete TC1 | 1. Open dashboard 2. Input new pass word 3. Confirm pass word 4. Click confirm | 1. Open dashboard 2. Input new pass word 3. Confirm pass word 4. Click confirm | Enter new pass = "" Enter confirm = "123" | Error message:Please fill out this field!!!!!! | Error message:Please fill out this field!!!!!! | Return page potential customer list | Pass | Average | 2020-03-23 | No
TC47 | LinhNC | Logout | Only one test case | Go to Login page | Complete TC1 | 1. Open dashboard 2. Click Logout in menu | 1. Open dashboard 2. Click Logout in menu | No | Go to login page | Go to login page | Go to login page | Pass | Average | 2020-03-23 | No

## Test GUI
GUI TESTING
|  |  | Tester: | Lâm Thị Khánh Hằng
Test result:
|  |  | Passed: | 32
|  |  | Failed: | 3
|  |  | Total testcase: | 35
ID | Test case | Test description | Result | Status | Date of the Test | Notes
GT01 | General GUI | General background color | Accordant | Passed | 26/03/2020 | Checked
|  | General font | Accordant | Passed | 26/03/2020 | Checked
|  | General font size | Accordant | Passed | 26/03/2020 | Checked
|  | Textbox setting | Accordant | Passed | 26/03/2020 | Checked
|  | All controls are align correctly | Correct | Passed | 26/03/2020 | Checked
|  | Message are shown correctly | Correct | Passed | 26/03/2020 | Checked
|  | Check if input are display correctly | Correct | Passed | 26/03/2020 | Checked
|  | All border are set | Accordant | Passed | 26/03/2020 | Checked
|  | Screen resolution are fixed | Fix with users | Passed | 26/03/2020 | Checked
|  | Display correctly in different browsers | Correct | Passed | 26/03/2020 | Checked
GT02 | Check validity | Maxlength and minimum length of data input | Some do not check data | Failed | 26/03/2020 | Checked
|  | Distinguish uppercase and lowercase letters | Checked | Passed | 26/03/2020 | Checked
|  | Check null | Checked | Passed | 26/03/2020 | Checked
|  | Check special characters | Checked | Passed | 26/03/2020 | Checked
|  | Check blank at the beginning/ending | Checked | Passed | 26/03/2020 | Checked
|  | Check blank input | Checked | Passed | 26/03/2020 | Checked
GT03 | Methods of migration web browsing | All web pages / windows are accessible from the menu | Checked | Passed | 27/03/2020 | Checked
|  | All windows are accessible from the toolbar | Checked | Passed | 27/03/2020 | Checked
|  | Check all the screens called from the button are displayed correctly | Checked | Passed | 27/03/2020 | Checked
|  | Message confirming page switch | Some don't have but accepted | Passed | 27/03/2020 | Checked
|  | When turning pages on the menu message confirming page switch | Some don't have but accepted | Passed | 27/03/2020 | Checked
GT04 | Program's friendliness | All list are sorted | Yes | Passed | 27/03/2020 | Checked
|  | The default is to sort by alphabel. Except where there is a specific sort request | Yes | Passed | 27/03/2020 | Checked
|  | Are all date values ​​formatted as required? | Yes | Passed | 27/03/2020 | Checked
|  | Are all on-screen buttons assigned with their respective shortcut keys? | No | Failed | 27/03/2020 | Checked
|  | Are all assigned keyboard shortcuts working correctly? | No | Failed | 27/03/2020 | Checked
|  | Check that all disable fields are unordered | Yes | Passed | 27/03/2020 | Checked
|  | Check if the focus position is set to the first field or the first control when the screen loads | Some don't have but accepted | Passed | 27/03/2020 | Checked
|  | In case of input error,When displaying error message, is there focus on error position after closing the message window? | Some don't have but accepted | Passed | 27/03/2020 | Checked
|  | In case of operation error, when displaying error msg, is there focus on previous position after closing popup window? | Some don't have but accepted | Passed | 27/03/2020 | Checked
|  | In case of calling popup window, after closing the window, will focus on the previous position or not | Some don't have but accepted | Passed | 27/03/2020 | Checked
|  | In case the popup window is not closed, focus is not allowed on the page that is processing the data | Some don't have but accepted | Passed | 27/03/2020 | Checked
GT05 | Check data binding | Data is saved when the window is closed | Yes | Passed | 27/03/2020 | Checked
|  | Check the maximum length of all fields, and make sure the characters are not cut off | Yes | Passed | 27/03/2020 | Checked
|  | Check the max / min value for numeric characters | Yes | Passed | 27/03/2020 | Checked